## Slide 1
Coordinator ECRAN KE 2
Ike van der Putte
Activity 1.2

## Slide 2
The activities for the period 2010-2013 (RENA) were based on a Multi Annual Work Plan with:
• Training and exchange,
• Institutional and methodological development,
• Cross border enforcement.
The activities planned under ECRAN will be built on the RENA results.
Since the work of inspectors and permit writers has to be more coordinated/ connected
to other activities within the environmental protection area, it has been decided that
ECENA under ECRAN should be of cross cutting nature.
This is particularly important as the work of ECENA is dealing with both implementation
and enforcement of the EU acquis. Cooperation with policy makers and law drafters has to
be strengthened in order to enable developing better implementable legislation.
Approach ECENA Work Plan Development 2013 -2016

## Slide 3
:
1.2.1 Capacity building on compliance with environmental legislation
1.2.2 External country assessments
1.2.3 Methodological development - application of IRAM/easy Tools
1.2.4 Compliance with REACH/CLP Regulations;
1.2.5 Trans frontier Shipment of Waste (TFS);
1.2.6 Inspection and enforcement in other policy areas;
1.2.7 Inspector’s participation in networking activities.
Activities/Tasks to be implemented

## Slide 4
No. | Date | Key outputs
1 | mid-January 2014 | Training Needs Questionnaire and Training Needs Assessment. Proposals for pilot industries for common inspection. TNA report
2 | January - February 2014 | Training Methodology, Training Programme and Training Materials
3 -10 | 8 Regional 3-day Training Workshops, April 1 2014 – May 2016 | Training IED, selected directives, common inspection with cross-cutting elements in Inspection management and planning, IED linkages with ambient water and -air quality, waste, EIA, chemicals and nature legislation. Training Report
Task 1.2.1 Capacity building on compliance with environmental legislation
The trainings (for inspectors and permit writers) are designed as a cross cutting activity,
in such a manner that the training programme will allow participation of policy makers
and legal drafters from other relevant WGs members such as Waste, Air, Water, etc.

## Slide 5
The scope and the list of acquis to be assessed should be determined in cooperation
with the beneficiaries and European Commission.
Specific attention for the functioning of the environmental inspection cycle.
This task will be closely coordinated with the activities related to compliance checks
(ECRAN Component 1, Activity 1.4) and screening reviews (ECRAN Component 2,
Activity 2.1).
This activity will be carried out “on request” i.e. if there is a request from the
Commission side or from the beneficiaries to check the level of implementation
and enforcement for a particular piece or pieces of EU legislation.
No. | Date | Key outputs
1 | January 2014- January 2016 | Up to eight Assessment Reports delivered and approved.
Task 1.2.2 External country assessments

## Slide 6
Task 1.2.3 Methodological development - application of IRAM/easy Tools
For SEVESO and IED the competent authority must draw up inspection
plans and programs for installations and establishments, including the
frequency of site visits.
These frequencies should be based on a systematic risk appraisal.
To disseminate the useful IMPEL IRAM easy tools methodology, up to 2 regional
trainings will be organised for all ECRAN beneficiary countries at a general level.
No. | Date | Key outputs
1 | 7,8 October 2014 | 2-day Regional Training Workshop 1, methodology, materials and report
2 | September 2015 | 2-day Regional Training Workshop 2, methodology, materials and report
3 | TBD | National training courses methodology, materials and reports (if requested)

## Slide 7
Task 1.2.4 Compliance with REACH/CLP Regulations
REACH and CLP are regulations and are therefore directly applicable. As they
enter into force, they will automatically form part of Member States’
national laws. In order to enable REACH and CLP to operate effectively in
practice, Member States are obliged to establish the necessary arrangements
for their implementation
The enforcement of the requirements of the REACH and CLP Regulations involves
different enforcement authorities and other bodies. The environmental
inspectorate can play a coordinating role.
No. | Date | Key outputs
1 | January-February 2015 | 2-day Regional Training Workshop 1, methodology, materials and report
2 | October - November 2015 | 2-day Regional Training Workshop 2, methodology, materials and report
3 | TBD | National training courses methodology, materials and reports (if requested)

## Slide 8
Task 1.2.5 Trans frontier Shipment of Waste (TFS)
To continue the work on what has been accomplished within RENA together
with IMPEL, it is proposed to organise up to 2 regional trainings combined with
a site visit to consolidate and increase the know-how and improve the required
institutional structures. Cooperation with IMPEL is again envisaged
No. | Date | Key outputs
1 | 2,3 July 2014 | 2-day Regional Training Workshop 1 (Croatia?), methodology, materials and report
2 | May 2015 | 2-day Regional Training Workshop 2, methodology, materials and report
3 | March 2016 | Report on study visit (1) to the selected EU MS Institution

## Slide 9
Task 1.2.6 Inspection and enforcement in other policy areas
The project team will aim to create links with other sector specific Working Groups
defined under Component 2 Environment in order to enhance the capacities of
inspections in sector specific areas
A clear connection can be made to the Nature WG, building on the activities delivered
under ECENA in this area in the previous period
No. | Date | Key outputs
1 | September – October 2014 | Regional Training Workshop 1 (Croatia?), methodology, materials and report
2 | February – April 2015 | Regional Training Workshop 2, methodology, materials and report
3 | September – October 2015 | Regional Training Workshop 3, methodology, materials and report
4 | January – February 2016 | Regional Training Workshop 4, methodology, materials and report

## Slide 10
Task 1.2.7 Inspectors participation in networking activities and
ECENA Coordinators Annual Meetings
IMPEL and IMPEL/GREENFORCE are the main networks that should be considered and
recommended. Membership of IMPEL is now open for all beneficiary
countries within the ECRAN programme. With IMPEL membership a more broad
participation of inspectors in the various clusters of IMPEL can be supported.
A new activity is proposed which considers the participation in the European Forum
of Judges for Environment (EUFJE)
Along the same lines, the newly established European Network of Prosecutors for the
Environment (ENPE) can be mentioned as a network that helps practitioners to connect
The practice established under RENA will continue under ECRAN when It comes to this
task. ECRAN will finance participation of up to one representative from the beneficiary
country to the relevant meetings of related networks. The request for financing will be
addressed to ECRAN Secretariat who will arrange the logistics upon approval of EC.
Considering enforcement in the European Union also EUROPOL/ENVICRIMENET
has to be mentioned as an important organisation
Other networks which are of secondary relevance are INTERPOL and INECE because of
their international perspective

## Slide 11
No. | Date | Key outputs
1 | January 2014 | ECENA WG Annual Meetings materials
2 | December 2014/January 2015 | ECENA WG Annual Meetings materials
3 | December 2015/January 2016 | ECENA WG Annual Meetings materials
4 | December 2013– September 2016 | Reports from the beneficiaries participating to the relevant meetings of the related networks.

## Slide 12
Thank you for your attention