## Slide 1: Work plan 2014
Activity 2.3: Water Management Working Group

## Slide 2: Tasks
2.3.1 Organisation of annual Working Group meetings
2.3.2 Assistance in the development of transboundary river basin management plans (RBMPs)
2.3.3 Economic analysis in accordance with the WFD (cost recovery and cost-effectiveness considerations), including innovative systems of waste water treatment
2.3.4 WFD and Marine Strategy Framework Directive – where to draw the line?

## Slide 3: Aim
Propose the activities to meet the tasks’ objectives;
Discuss and agree on subsequent steps;
Aligne tasks within time frame.

## Slide 4: 2.3.1 Organisation of annual Working Group meetings
Objectives: Effective planning and reporting on progress achieved within planned period
Expected outputs:
Bringing together relevant representatives of the beneficiary countries;
Discussing the needs of particular countries and the ways how the ECRAN project could address them best;
Adopting Work Plan and other documents;
Exchanging information among all countries on progress in the implementation of the work plan discussing bottle-neck and the ways to solve them.
No. | Date | Key outputs
1 | end-December 2013 | Detailed work plan, agenda and background materials
2 | February 10, 2014 | Annual Meeting of WMNCs

## Slide 5: 2.3.2 Assistance in the development of transboundary RBMPs
Objective: Provide practical assistance to the beneficiary countries in concrete steps for development of the RBMP at the selected pilot site
No. | Date | Key outputs
1 | end-December 2013 | Draft criteria for selection of a pilot river basin
2 | mid-January 2013 | Draft Proposal for specific RBMP development topic
3 | February 2014 | Selection of pilot river basin received from the WMNCs;
4 | February – March 2014 | Search for the STE and her/his recruitment
5 | March – April 2014 | Selection of specific RBMP development topic made and approach prepared; Participants to the pilot river basin from the Beneficiary countries identified
6 | mid-May 2014 | Screening workshop at pilot river basin (pilot – countries)
7 | September 2014 | Training need assessment prepared (in cooperation with TAIEX)
8 | October – November 2014 | Detailed regional training plan including study visit programme, agenda and background materials prepared (in cooperation with TAIEX and agreed
9 | December 2014 | 1st Regional training seminar (all countries) on RBMP held

## Slide 6: Expected outputs
Criteria for selection and selection of the river basin that will be used as pilot case;
Selection of the specific RBMP development topic in coordination with the beneficiaries;
Development of detailed regional training plan including the study visit programme;
Regional training programme and study visit delivered, training materials published on ECRAN website.

## Slide 7: Main criteria for selection of pilot RB
Trans-boundary characteristic - RB shared by two or more Beneficiary countries.
Even distribution distributed
The implementation of the WFD in progress and/or national legislation is fully harmonised with WFD
Legislation framework for RBMP
Data/information for selected specific topic is available.
Willingness to share and exchange data/information and knowledge.

## Slide 8: Additional criteria for selection of pilot river basin
Professional staff for drafting RBMP exclusively in charge.
Willingness to learn something new, to gather experience and share the process with other ECRAN beneficiaries;
National/institutional funding preparation of RBMPs is secured for coming 3 years

## Slide 9: Candidates for pilot river basin
VARDAR/AXIOS
MARITSA/EVROS/MERIÇ
STRUMA/STRYMONAS
DRIM/DRIN
DRINA RIVER

## Slide 10: Specific topic
RBMP compliance:
  Strengths;
  Weaknesses;
  Gaps.
Programme of Measures (PoM) - Framework for the preparation of acceptable and efficient POMs:
  Framework for the assessment and establishment of the link between water status, pressures and impact of the pressures on water status;
  Extension of the status-pressure-impact link to the simulation of the expected effects of PoM implementation;
  Expected effects of the implementation of the PoM on pressures for basic and supplementary measures;
  Role of monitoring.

## Slide 11: Proposal of specific RBMP development topics
Management of uncertainties in RBMPs related to:
  Characterisation of the RBDs;
  Remaining uncertainty in the application of the intercalibration process;
  Assessment of water bodies status;
  Assessment of effect of potential measures.

## Slide 12: 2.3.3 Economic analysis in accordance with the WFD
Objectives: Capacity building - provide practical knowledge on the current status of the implementation of key principles of Article 9 of the WFD, and in particular on the cost-recovery principle through water pricing.
No. | Date | Key outputs
1 | January – February 2014 | Proposal and approach to the EA theme
2 | March 2014 | EA theme for regional training selected and approved
3 | April 2014 | Questionnaire for assessment prepared and submitted to the Beneficiaries
4 | June – August 2014 | Assessment and result reported (in cooperation with TAIEX)
5 | September 2014 | Introductory workshop on EA including exchange of experience of MS
6 | October 2014 | Training need assessment prepared (in cooperation with TAIEX)
7 | November – December 2014 | Detailed regional training plan, agenda and background materials prepared (in cooperation with TAIEX) and agreed

## Slide 13: Expected outputs
Two regional seminars organised: The themes related to “Economic analysis in accordance with the WFD:
  Recovery of the costs through water pricing,
  An institutional and policy framework of the water utility sector for cost recovery and efficiency
Assessment report on readiness of ECRAN Beneficiaries for EAs;
Regional training reports and training materials published on ECRAN website.

## Slide 14: 2.3.4 WFD and Marine Strategy Directive – where to draw the line?
Objective: To encourage and improve dialogue and coordination between beneficiaries’ experts in the international river basin, the several, country specific, topics are proposed and one should be selected for tailor made training
No. | Date | Key outputs
1 | March 2014 | Proposal for topic for the regional training
2 | April 2014 | Selection the topic for regional training made
3 | June – July 2014 | Training need assessment prepared (in cooperation with TAIEX)
4 | September - October 2014 | Detailed regional training plan, agenda and background materials prepared (in cooperation with TAIEX) and agreed
5 | November 2014 | Regional training seminar on WFD and MSFD held (in cooperation with TAIEX)
6 | December 2014 | Prepare selection criteria for specific and tailored made training topic

## Slide 15: Expected outputs
Regional, tailored made training plan for country specific theme related to the key points of Integrated Coastal Zone Management and Marine Strategy Framework Directive prepared.
Training delivered.
Regional training report and training materials published on ECRAN website