## Slide 1: Overview of activities
Martin Smutny, KE3, ECRAN
EA WG 2nd Annual Meeting
November 26, 2014

## Slide 2: Key focus within the last period
Task 2.4.2: Planning and conducting support to SEA Pilot (Montenegro)
Task 2.4.3: Preparation and conducting joint regional workshop on SEA/EIA and Appropriate Assessment
Task 2.4.4: Preparation and conducting the 1st Training of Trainers (ToT)

## Slide 3: Task 2.4.1: Annual meeting
1st Annual meeting organized in Istanbul (November 2013)
Agreement on
  Activities of the EC WG
  Criteria for SEA pilot selection
  Work plan for 2013 and 2014
Organized back-to-back with the International EIA Congress in Turkey with ECRAN session

## Slide 4: Task 2.4.2: SEA pilot
November 2013: Criteria for selection of pilot sites developed and circulated
January – March 2014: Pre-selection of SEA pilot
April 2014: Confirmation of 1st SEA pilot and initiating the support

## Slide 5: Task 2.4.2: SEA pilot
SEA for Offshore hydrocarbons exploitation and production programme in Montenegro
Role of ECRAN:
  Providing continuous quality assurance throughout the SEA pilot i.e. reviewing each main stage/analysis of SEA against SEA quality criteria
  Providing assistance with transboundary consultations (if needed)
Agreement with the Ministry of Economy was made April/May 2014
Activities initiated late June / July 2014

## Slide 6: Task 2.4.2: SEA pilot
Altogether 4 Interim Reports were drafted
  1st IR (July 2014) providing a feedback on proposed scope of SEA and Gap Analysis
  2nd IR (July 2014) addressing the draft Scoping Report
  3rd IR (August 2014) focusing on the initial description of baseline situation
  4th IR (September 2014) evaluating the final draft Scoping Report including stakeholders´ engagement plan

## Slide 7: Task 2.4.2: SEA pilot
A number of recommendations provided, many of them integrated by SEA experts e.g.
  Several additional issues included for further analyses (and relevant indicators)
  More details on planned offshore development provided
  Likely transboundary impacts addressed
  Structure of Scoping Report enhanced

## Slide 8: Task 2.4.3: Joint regional workshop on SEA/EIA and AA
Activities (carried out in cooperation with Nature WG) during June – September 2014
  Developing detailed agenda and draft presentations
  Approaching TAIEX experts
  Distributing invitations
Conducted in October 30 – 31, 2014, Zagreb

## Slide 9: Task 2.4.3: Joint regional workshop on SEA/EIA and AA
High level involvement of experts from Croatia and Slovenia
Experience and practical aspects presented from those counties + Czech Republic, UK
The most relevant for Montenegro and Serbia, other countries are still at the very beginning of establishing N2K and AA systems
AA linked to SEA/EIA processes (partially or fully) will be more efficient in ECRAN countries context rather than separate AA procedure.

## Slide 10: Task 2.4.4: Training of Trainers
Preparatory activities
  Selecting participants based on nominations and selection criteria (April 2014)
  Preparing detailed agenda (April 2014)
  Identification of TAIEX experts
  Preparing training manual and presentations with inputs from TAIEX and ECRAN experts (July – August 2014)
  Inviting participants and distributing the training manual (September 2014)

## Slide 11: Task 2.4.4: Training of Trainers
1st ToT conducted September 23 – 26, Podgorica
Facilitated by 2 ECRAN + 3 TAIEX experts covering
  SEA/EIA expertise
  Training skills
Participants actively involved
Sections of country-specific training materials were prepared
Extensive knowledge of the topic, while training skills still need to be enhanced

## Slide 12: Main achievement and key challenges
Integrating ECRAN inputs to SEA pilot
Successful 1st ToT and joint AA workshop
X  Readiness for local SEA/EIA trainings
Identification of 2nd SEA pilot
Joint ´tri-lateral´ workshop for SEA/EIA, AA and WFD

## Slide 13: Thank you for your attention!