## Slide 1: EA WG Workplan for 2015
Martin Smutny, KE3, ECRAN
EA WG 2nd Annual Meeting
November 26, 2014

## Slide 2: Task 2.4.1: Annual Meetings
3rd Annual Meeting (Vienna)
  October 2015: agenda distributed
  November 2015 (end): annual meeting organized

## Slide 3: Task 2.4.2: Implementation and monitoring of SEA Directive
SEA pilot in Montenegro
  December 2014: QA of the SEA report
  January 2015: Final workshop and presentation of QA results
  February 2015: Final QA report
2nd SEA pilot
  December 2014: suggestions by countries
  January 2015: selection of 2nd pilot
  By December 2015: support to be provided

## Slide 4: Task 2.4.3: Other environmental assessments
Project proposal
  2 regional trainings on SEA/EIA in Nature and Water areas
  1 joint regional training (Nature, Water and EA WGs)
Proposed change
  2 regional trainings on SEA/EIA and AA
  1 regional training on SEA/EIA in Water area

## Slide 5: Task 2.4.3: Other environmental assessments
2nd regional training on SEA/EIA and AA
  June 2015: Agenda distributed
  September 2015: Training materials developed
  October 2015: Training organized
Regional training on SEA/EIA in Water area
  April 2015: Agenda distributed
  May 2015: Training materials developed
  June 2015: Training organized

## Slide 6: Task 2.4.3: Other environmental assessments
3 regional trainings on SEA/EIA for specific economic sectors / policy areas
  October 2015: Request for suggesting sectors/policy areas distributed (together with the agenda for the 3rd Annual meeting)
  November 2015 (end): Preliminary selection of sectors/policy areas and schedule discussed at the 3rd Annual meeting
  December 2015: Final version of sectors/policy areas selected and trainings schedule distributed (together with minutes of the 3rd Annual meeting)

## Slide 7: Task 2.4.4: Train the trainers
Trainings in ECRAN countries
  Should cover entire SEA or EIA topic
  Based on materials developed at the 1st ToT
  ToT participants should play major role
  ECRAN will provide support in designing the agenda, delivering presentations on certain topics and/or co-facilitating some sections

## Slide 8: Task 2.4.4: Train the trainers
Trainings in ECRAN countries, 1st round
  Dec 2014: Detailed schedule of local trainings for 2015 finalized
  Jan 2015: Agenda and outline of training materials for local training in March – May 2015 ready
  Feb 2015: Training materials for local training in March – May 2015 ready
  March – May 2015: Trainings organized

## Slide 9: Task 2.4.4: Train the trainers
Trainings in ECRAN countries , 1st round
  March 2015: SEA workshop (2 days) for sectoral ministries, practitioners, NGOs in Albania
  April 2015: Workshop (2 days) in Croatia on ....
  May 2015: Workshop (2 days) in Serbia on ...
  March 2015

## Slide 10: Task 2.4.4: Train the trainers
Trainings in ECRAN countries, 2nd round
  August 2015: Agenda and outline of training materials for local training in October – December 2015 ready
  September 2015: Training materials for local training in October – December 2015 ready
  October – December 2015: Trainings organized

## Slide 11: Task 2.4.4: Train the trainers
Trainings in ECRAN countries , 2nd round
  October 2015: SEA workshop (2 days) in Montenegro
  November 2015: Workshop (2 days) in Turkey on ....
  December 2015: ...

## Slide 12: Task 2.4.4: Train the trainers
2nd ToT
  June 2015: Agenda and outline of training materials distributed
  August 2015: Training materials prepared
  September 2015: 2nd ToT organized

## Slide 13: Discussion
Questions, comments, suggestions?

## Slide 14: Thank you for your attention!