## Timetable of Activities
|  | 2013 |  |  | 2014 | [12 empty] | 2015
Activity 2.4 Environmental Assessments Working Group |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March
Task 2.4.1 | Organisation of annual Working Group meetings
Task 2.4.2 | Implementation and monitoring of SEA Directive
Task 2.4.3 | Other environmental assessments
Task 2.4.4 | Train trainers programme on the EIA and SEA
Notes and comments |  |  | Annual meeting, Nov 7, Istanbul | Preliminary selection of SEA pilots |  | Defintion of training programme, agenda, selection criteria for trainees | Selection of pilot sites, meetings with planning agencies |  | Selection of trainees |  | ToT (Montenegro) | Preparation of training materials |  | Training on SEA/EIA and Appropriate Assessment (Croatia) | Local trainings